## Sheet1
Sr No. | Task name | Description | Status | Start Date | End Date
1 | download and load dataset | 1- Download the dataset from kaggle link(https://www.kaggle.com/datasets/shubhambathwal/flight-price-prediction?select=Clean_Dataset.csv) 2 - Load the data set to the S3 bucket(snowflakesprint1) | Complete | 23/04/2022 | 23/04/2022
2 | create a database | Create a database SF_Project | Complete | 23/04/2022 | 23/04/2022
3 | create a schema | Create a schema ITR_RDS / ITR_RDS_Landing | Complete | 23/04/2022 | 23/04/2022
4 | create a datamart schema | Create a datamart schema - ITR_DM | Complete | 23/04/2022 | 23/04/2022
5 | create a table | Create a table FLIGHT and FLIGHT_SCD as per the data set | Complete | 23/04/2022 | 23/04/2022
6 | create an external stage | Create external stage FLIGHT_STAGE_1 and FLIGHT_STAGE_2 for loading the data structure | Complete | 23/04/2022 | 23/04/2022
7 | create a snowpipe | Create Snowpipe FLIGHT_PIPE and FLIGHT_PIPE_SCD for auto ingesting data from S3 bucket snowflakesprint1 | Complete | 23/04/2022 | 23/04/2022
8 | create a stream | Create stream FLIGHT_STREAM on table FLIGHT_SCD | Complete | 23/04/2022 | 23/04/2022
9 | create SCD | Perform SCD Type-2 operation on consumer table TARGET_FLIGHT as per changes happen in the source table FLIGHT_SCD | Complete | 23/04/2022 | 23/04/2022
10 | create a task | Automate data load from snowpipe to consumer table TARGET_FLIGHT on everyday at 12 pm | Complete | 24/04/2022 | 24/04/2022
11 | Data Analysis | Perform the below analysis on the Data set- 1. which airline have maximum fights in the morning and Early_morning 2. does the flights with one and more than one stops have less price compared to flights with zero stops 3. Average travel duration for flights with one and more than one stops 4. Which airlines makes highest selling for Afternoon flights 5. which sourc to destination flight fare is less | Complete | 24/04/2022 | 24/04/2022